## EXAMPLE - Agile Project Plan
Team software engineering project plan
| PROJECT NAME | Team software engineering banking system |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Joe |  |  | 2025-09-02 | 2025-05-09 | 85% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 | Account management | Everyone | One | 2024-02-21 | 2024-03-06 | 15 | Complete | All account management features have been fully implemented and tested
No | Feature 1 | Create and set up a new banking account (personal/business) | Joe, Lewis | One | 2024-02-21 | 2024-03-06 | 15 | Complete
No | Feature 2 | Edit account details (e.g. user information, account type) | Joe, Sam | One | 2024-02-21 | 2024-03-06 | 15 | Complete
No | Feature 3 | Delete a user | Joe, John | One | 2024-02-21 | 2024-03-06 | 15 | Complete
No | SPRINT 2 | Financial transactions | Everyone | Two/Three | 2024-03-13 | 2024-03-27 | 15 | Complete | Added all transaction functionality
No | Feature 4 | Withdraw cash with real-time balance update | Everyone | One | 2024-03-13 | 2024-03-27 | 15 | Complete
No | Feature 5 | Deposit cash with reciept generation | Joe, Sam | One | 2024-03-13 | 2024-03-27 | 15 | Complete
No | Feature 6 | Transfer funds between different accounts within the same bank | Sam,John | Two | 2024-03-13 | 2024-03-27 | 15 | Complete
No | Feature 7 | Implement transaction history with filters (data, type, amount) | Sam, John | Two | 2024-03-13 | 2024-03-27 | 15 | Complete
No | SPRINT 3 | Security and compliance | Everyone | Three/Four | 2024-03-20 | 2024-04-24 | 36 | Complete
No | Feature 8 | Comply with relevant financial regulations and data protection laws | Everyone | Three | 2024-03-20 | 2024-04-24 | 36 | Complete | Everyone helped in overseeing that financial and data protection laws were followed
No | Feature 9 | Esnure data encryption for sensitive information |  |  | 2024-03-20 | 2024-04-24 | 36 | Complete
No | Feature 10 | Implement robust authentication mechansims |  |  | 2024-03-20 | 2024-04-24 | 36 | Complete
Yes | SPRINT 4 | Account services | Everyone | Two/Three | 2024-04-03 | 2024-04-17 | 15 | Needs Review
No | Feature 11 | View detailed account information including current balance, recent transactions and account type |  | One | 2024-04-03 | 2024-04-17 | 15 | Complete
No | Feature 12 | Set up and manage recurring payments and direct debts |  | Three | 2024-04-03 | 2024-04-17 | 15 | Overdue
No | Feature 13 | Request and manage services like checkbooks and debit/credit cards |  | Three | 2024-04-03 | 2024-04-17 | 15 | Overdue
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)

## BLANK - Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME |  |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | [6 empty] | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
| SPRINT 1 |  |  |  | 0 | 0
Feature 1
Feature 2
Feature 3
| SPRINT 2 |  |  |  | 0 | 0
Feature 4
Feature 5
Feature 6
| SPRINT 3 |  |  |  | 0 | 0
Feature 7
Feature 8
Feature 9
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold