## EXAMPLE - Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | Product Release |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Alex B. |  |  | 2025-09-02 | 2025-10-10 | 35% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 |  | Alex B. |  | 2025-09-03 | 2025-09-13 | 11
Yes | Feature 1 |  | Frank C. |  | 2025-09-03 | 2025-09-07 | 5 | Complete
No | Feature 2 |  | Jacob S. |  | 2025-09-07 | 2025-09-12 | 6 | In Progress
No | Feature 3 |  | Jacob S. |  | 2025-09-09 | 2025-09-13 | 5 | Overdue
No | SPRINT 2 |  | Jacob S. |  | 2025-09-16 | 2025-09-24 | 9
No | Feature 4 |  | Alex B. |  | 2025-09-16 | 2025-09-17 | 2 | Approved
Yes | Feature 5 |  | Frank C. |  | 2025-09-17 | 2025-09-21 | 5 | Needs Review
No | Feature 6 |  | Shari W. |  | 2025-09-22 | 2025-09-24 | 3 | On Hold
No | SPRINT 3 |  | Shari W. |  | 2025-09-24 | 2025-10-05 | 12
No | Feature 7 |  | Alex B. |  | 2025-09-25 | 2025-09-29 | 5 | Not Started
No | Feature 8 |  | Kennedy K. |  | 2025-09-24 | 2025-10-02 | 9 | Not Started
No | Feature 9 |  | Jacob S. |  | 2025-10-02 | 2025-10-05 | 4 | Not Started
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)

## BLANK - Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME |  |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | [6 empty] | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
| SPRINT 1 |  |  |  | 0 | 0
Feature 1
Feature 2
Feature 3
| SPRINT 2 |  |  |  | 0 | 0
Feature 4
Feature 5
Feature 6
| SPRINT 3 |  |  |  | 0 | 0
Feature 7
Feature 8
Feature 9
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold